RationSeva – Online Ration Card Services Portal

Change Management Process

Handling state eligibility-rule changes after go-live
Case Study No. 142 | District Supply Office | Version 1.0 | Oct 2026

# 1. Why This Process Is Needed

The state is expected to change eligibility rules within the year. This risk has P = 0.5, I = 7 and exposure 3.5 (ranked #2). Uncontrolled edits would break the eligibility checks and the audit trail.

# 2. Roles

| Role | Who | Responsibility |
| --- | --- | --- |
| Requester | State Dept. / DSO staff | Raises a change request (CR) with a copy of the GO |
| Change Coordinator | Project Manager | Logs the CR, tracks it to closure |
| Impact Analyst | Business Analyst + Tech Lead | Assesses scope, time, cost and quality |
| Decision Owner | District Supply Officer | Approves, rejects or defers the change |
| Implementer | Admin (config) / Developer (code) | Applies the change as a new rule version |
| Verifier | Tester + 1 Officer | Runs regression tests and signs off |

# 3. Change Categories

| Type | Example | Path | Target time |
| --- | --- | --- | --- |
| A – Configuration | Change income limit or document list | Fast track: Admin creates a new rule version | <= 1 working day |
| B – Logic | New condition or new field | Full process + code release | <= 10 working days |
| C – New service | New request type | Treated as a new project or phase | Planned release |

# 4. Six-Step Procedure

Figure 1: Rule-change process

| Step | What happens | Output |
| --- | --- | --- |
| 1. Capture | Requester fills in the CR form (GO no., rule, old/new value, effective date) | CR-ID in change log |
| 2. Understand reason | Coordinator confirms the legal source and urgency with the State Dept. | Reason + priority |
| 3. Analyse impact | Assess Scope (screens, rules), Time (days), Cost (effort), Quality (tests to rerun) | Impact sheet |
| 4. Decide | District Supply Officer approves, rejects or defers | Decision + date |
| 5. Update plan | Update the SRS rule table, schedule, test cases and traceability matrix | Updated baseline |
| 6. Implement & verify | New rule version with effective date; rerun decision-table and BVA tests; officer sign-off; SMS/notice to staff | Rule vX.Y live, CR closed |

Note: Requests already submitted are evaluated under the rule version that was active on the submission date. This is fair to applicants and keeps the audit trail intact.

# 5. Change Log

| CR | Date | Change & reason | Impact (S / T / C / Q) | Decision | Implemented & verified | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CR-001 | 05-Jan-27 | PHH income limit ₹1,00,000 → ₹1,20,000 (State GO 12/2027) | S: 1 rule value; T: 0.5 d; C: ~0.5 person-day; Q: rerun TC-06, TC-12 at new boundary | Approved – DSO, 06-Jan | Rules v1.1, effective 01-Feb; tests passed 07-Jan | Closed |
| CR-002 | 20-Feb-27 | Aadhaar of new member mandatory for Add Member (anti-fraud GO) | S: +1 field, +1 condition; T: 3 d; C: ~3 person-days; Q: update DT-2, TC-07 | Approved – DSO, 22-Feb | Release 1.2 on 02-Mar; regression passed | Closed |
| CR-003 | 10-Mar-27 | Add 'Card Surrender' request type | S: new service; T: ~10 d; C: high; Q: new test suite | Deferred to Phase 2 | – | Deferred |